## SEGUIMIENTO GTS
BASE DE DATOS SEGUIMIENTO GTS
|  |  | Greenfield Colombia | [9 empty] | GTS BREWING
#GTS | GTS | GESTOR | Aplica? (marque X) |  | Totales |  | Completadas | Requeridas | Faltantes | Cerradas | Mandatorio | Avance
0 | Fire SAFETY | [7 empty] | 0
| 01. GTS 3C Brewing |  |  | 89.36% | General Areas Safety | 92.63% | Recibo de Granos | 23 | 2 | 21 | 0 | 91.3%
[7 empty] | Silos | 22 | 2 | 20 | 1 | 90.91%
[7 empty] | Torre de molienda | 29 | 2 | 27 | 0 | 93.1%
[7 empty] | Brewhouse | 41 | 5 | 36 | 2 | 87.8%
1 |  | Cristain Brochero | X |  |  |  | Cold Block | 38 | 2 | 36 | 0 | 94.74%
#REF! | [6 empty] | CCTs | 29 | 4 | 25 | 1 | 86.21%
#REF! | [6 empty] | Filtración | 39 | 3 | 36 | 1 | 92.31%
#REF! | [6 empty] | BBTs | 28 | 4 | 24 | 1 | 85.71%
#REF! | [6 empty] | Dosificación de azúcar | 35 | 5 | 30 | 1 | 85.71%
#REF! | [6 empty] | Edificio Aditivos | 29 | 5 | 24 | 1 | 82.76%
#REF! | [6 empty] | Almacenamiento de Lupulo | 24 | 3 | 21 | 0 | 87.5%
#REF! | [6 empty] | Corredor de válvulas | 24 | 3 | 21 | 1 | 87.5%
#REF! | [6 empty] | Subestación electrica Filtración | 25 | 4 | 21 | 0 | 84%
#REF! | [6 empty] | Zona Subproductos | 18 | 2 | 16 | 1 | 88.89%
[7 empty] | Total | 404 | 46 | 358 | 10 | 88.61%
#REF! |  |  |  |  | Grains Handling | 94.15% | InTake Arroz | 41 | 2 | 39 | 0 | 95.12%
#REF! | [6 empty] | In take Malta | 41 | 2 | 39 | 0 | 95.12%
#REF! | [6 empty] | Silos | 42 | 4 | 38 | 1 | 90.48%
#REF! | [6 empty] | Torre de Molienda | 47 | 2 | 45 | 0 | 95.74%
[7 empty] | Total | 171 | 10 | 161 | 1 | 94.15%
#REF! |  |  |  |  | Brew Hot Block | 95.33% | Brewhouse | 45 | 2 | 43 | 0 | 95.56%
#REF! | [6 empty] | Sugar Dosing | 23 | 1 | 22 | 0 | 95.65%
#REF! | [6 empty] | Co-products | 21 | 1 | 20 | 0 | 95.24%
[7 empty] | Energy Recovery | 18 | 1 | 17 | 0 | 94.44%
[7 empty] | Total | 107 | 5 | 102 | 0 | 95.33%
[5 empty] | Brew Cold Bock | 80.16% | Yeast Storage | 13 | 3 | 10 | 1 | 76.92%
[7 empty] | Propagation | 13 | 3 | 10 | 1 | 76.92%
[7 empty] | Waste Yeast | 15 | 3 | 12 | 1 | 80%
[7 empty] | Opticellar | 19 | 3 | 16 | 1 | 84.21%
[7 empty] | CCT | 16 | 3 | 13 | 0 | 81.25%
[7 empty] | Filtration | 14 | 3 | 11 | 1 | 78.57%
[7 empty] | BBT | 16 | 3 | 13 | 0 | 81.25%
[7 empty] | DAW | 13 | 3 | 10 | 1 | 76.92%
[7 empty] | CIP | 7 | 1 | 6 | 1 | 85.71%
Total | [6 empty] | Total | 126 | 25 | 101 | 7 | 80.16%
[5 empty] | Total |  |  | 808 | 86 | 722 | 18 | 89.36%
| 02. GTS 3C Utilities |  |  | 93.94% | General Areas Safety | 96.55% | Sala de máquinas NH3 | 42 | 4 | 38 |  | 90.48%
[7 empty] | Sala de máquinas Aire | 36 | 0 | 36 |  | 100%
[7 empty] | Sala de máquinas CO2 | 35 | 1 | 34 |  | 97.14%
[7 empty] | Calderas | 32 | 0 | 32 |  | 100%
[7 empty] | Total | 145 | 5 | 140 |  | 96.55%
[5 empty] | Área de Procesos | 91.69% | Calderas | 138 | 18 | 120 |  | 86.96%
[7 empty] | Área CO2 - Compressor | 27 | 3 | 24 |  | 88.89%
[7 empty] | Compressed air Safety | 23 | 0 | 23 |  | 100%
[7 empty] | Refrigeration - Utilidad área | 66 | 6 | 60 |  | 90.91%
[5 empty] | General Machine Safety | 93.57% | Condensadores evaportativos | 28 | 6 | 22 |  | 78.57% |  |  | #REF! | #REF! | #REF! | #REF!
[7 empty] | Compresores NH3 Vacio | 28 | 6 | 22 |  | 78.57%
[7 empty] | Compresor NH3 Tornillo (ssu) | 28 | 6 | 22 |  | 78.57%
[7 empty] | Chiller de agua helada | 18 | 2 | 16 |  | 88.89%
[7 empty] | Chiller DAW 1 | 18 | 2 | 16 |  | 88.89%
[7 empty] | Chiller DAW 2 | 18 | 2 | 16 |  | 88.89%
[7 empty] | Chiller Glicol | 18 | 2 | 16 |  | 88.89%
[7 empty] | Tranfer cooler 1 | 18 | 2 | 16 |  | 88.89%
[7 empty] | Tranfer cooler 2 | 18 | 2 | 16 |  | 88.89%
[7 empty] | CO2 vaporizer Vaporizador de CO2 | 17 | 2 | 15 |  | 88.24%
[7 empty] | Bombas de glicol | 28 | 3 | 25 |  | 89.29%
[7 empty] | Bombas de agua | 28 | 3 | 25 |  | 89.29%
[7 empty] | OSM (Sistema de envío diésel calderas) | 23 | 1 | 22 |  | 95.65%
[7 empty] | Sistema de llenado tanques diésel | 23 | 1 | 22 |  | 95.65%
[7 empty] | Tanque 2 almacenamiento diésel | 21 | 1 | 20 |  | 95.24%
[7 empty] | Tanque 1 almacenamiento diésel | 21 | 1 | 20 |  | 95.24%
[7 empty] | Caldera 4 | 27 | 1 | 26 |  | 96.3%
[7 empty] | Caldera 3 | 27 | 1 | 26 |  | 96.3%
[7 empty] | Caldera 2 | 27 | 1 | 26 |  | 96.3%
[7 empty] | Caldera 1 | 27 | 1 | 26 |  | 96.3%
[7 empty] | Distribuidor de vapor | 11 | 1 | 10 |  | 90.91%
[7 empty] | Desaireadro completo | 24 | 1 | 23 |  | 95.83%
[7 empty] | Suavizador | 25 | 1 | 24 |  | 96%
[7 empty] | CO2 storage tank Tanque de almacenamiento de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 evaporator Evaporador de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 pressure reducing station Estación reductora de presión de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 polishing filter Filtro de pulido de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 tank Tanque CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 cylinder filling station Estación de llenado de cilindros de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | CO2 truck filling pump Bomba de llenado de camión de CO2 | 27 | 0 | 27 |  | 100%
[7 empty] | Air dryer Secador | 33 | 1 | 32 |  | 96.97%
[7 empty] | Air filter Filtro de aire | 33 | 1 | 32 |  | 96.97%
[7 empty] | Storage tank Tanque de almacenamiento | 33 | 1 | 32 |  | 96.97%
[7 empty] | Total | 809 | 52 | 757 |  | 93.57%
[5 empty] | Total |  |  | 1208 | 84 | 1124 |  | 93.05%
|  |  |  | 100% | Areas Safety | 100% | Areas Safety | 38 | 0 | 38 | 2 | 100%
| GTS 3C Packaging.xlsx | [5 empty] | Linea RGB | 56 | 0 | 56 | 1 | 100%
[7 empty] | Linea CAN | 55 | 0 | 55 | 1 | 100%
[7 empty] | Total | 149 | 0 | 149 | 4 | 100%
[5 empty] | General Machine Can Line Safety | 100% | Transporte lata | 37 | 0 | 37 | 0 | 100%
[7 empty] | Transporte Paquetes | 40 | 0 | 40 | 0 | 100%
[7 empty] | Etiqueteadora | 43 | 0 | 43 | 0 | 100%
[7 empty] | Pasteurizador | 43 | 0 | 43 | 0 | 100%
[7 empty] | Rinser | 43 | 0 | 43 | 0 | 100%
[7 empty] | Variopack FS | 43 | 0 | 43 | 0 | 100%
[7 empty] | Variopack TFS | 43 | 0 | 43 | 0 | 100%
[7 empty] | Envolvedoras | 43 | 0 | 43 | 0 | 100%
[7 empty] | Llenadora | 43 | 0 | 43 | 0 | 100%
[7 empty] | Multiempacadora | 37 | 0 | 37 | 0 | 100%
[7 empty] | Inspectores | 39 | 0 | 39 | 0 | 100%
[7 empty] | Total | 454 | 0 | 454 | 0 | 100%
[5 empty] | General Machine RGB Safety | 100% | Despaletizadora | 44 | 0 | 44 | 0 | 100%
[7 empty] | Desempacadora | 41 | 0 | 41 | 0 | 100%
[7 empty] | Lavadora de cajas | 35 | 0 | 35 | 0 | 100%
[7 empty] | Lavadora de botellas | 39 | 0 | 39 | 0 | 100%
[7 empty] | Llenadora | 42 | 0 | 42 | 0 | 100%
[7 empty] | Pasteurizadora | 36 | 0 | 36 | 0 | 100%
[7 empty] | Etiqueteadora | 42 | 0 | 42 | 0 | 100%
[7 empty] | Paletizadora | 45 | 0 | 45 | 0 | 100%
[7 empty] | Inspectores (lineatronic) | 38 | 0 | 38 | 0 | 100%
[7 empty] | Total | 362 | 0 | 362 | 0 | 100%
| Environment |  |  | 52.68% | General Areas Safety | 72.38% | WTP | 37 | 12 | 25 |  | 67.57% |  | 6
[7 empty] | BTS | 40 | 12 | 28 |  | 70%
[7 empty] | Water Intake | 28 | 5 | 23 |  | 82.14%
[7 empty] | Total | 105 | 29 | 76 |  | 72.38%
[5 empty] | General Machine Safety | 32.98% | DAF | 16 | 10 | 6 |  | 37.5%
[7 empty] | Drum Screen | 19 | 13 | 6 |  | 31.58%
[7 empty] | Screw Press | 23 | 16 | 7 |  | 30.43% | GTS EDIFICIOS - CIVIL - ÁREAS GENERALES
[7 empty] | Clarifier Scrapper | 18 | 12 | 6 |  | 33.33%
[7 empty] | Dehumidifier | 18 | 12 | 6 |  | 33.33%
[7 empty] | Total | 94 | 63 | 31 |  | 32.98%
| Logistics |  |  | 87.38% | Logistica Safety | 83.33% | Bahias de carga | 19 | 2 | 17 |  | 89.47%
[7 empty] | Reparación de estibas | 10 | 1 | 9 |  | 90%
[7 empty] | Bodega PT | 12 | 2 | 10 |  | 83.33%
[7 empty] | Parqueadero de montacargas | 12 | 1 | 11 | 12 | 91.67%
[7 empty] | Muelles de descarga materiales | 11 | 1 | 10 |  | 90.91%
[7 empty] | Porteria Logística | 6 | 1 | 5 |  | 83.33%
[7 empty] | Parqueadero T1 | 11 | 2 | 9 |  | 81.82%
[7 empty] | Bascula | 7 | 1 | 6 |  | 85.71%
[7 empty] | Almacen de quimicos | 6 | 1 | 5 |  | 83.33%
[7 empty] | Almacenaniento de materiales de empaque | 6 | 1 | 5 |  | 83.33%
[7 empty] | Logistics Safety Warehouse | 26 | 8 | 18 |  | 69.23%
[7 empty] | Total | 126 | 21 | 105 |  | 83.33%
[5 empty] | General Areas Safety | 91.43% | General Areas Safety | 35 | 3 | 32 |  | 91.43%
[7 empty] | Total | 161 | 24 | 137 |  | 87.38%
| Obra Civil |  |  | 86.5% | Obra Civil Safety |  | Laboratorio Central | 16 | 1 | 15 |  | 93.75%
[7 empty] | Packahing Services | 24 | 1 | 23 |  | 95.83%
[7 empty] | Envasado | 30 | 3 | 27 |  | 90%
[7 empty] | Isla de Químicos Envasado | 22 | 4 | 18 |  | 81.82%
[7 empty] | WTP | 30 | 8 | 22 |  | 73.33%
[7 empty] | BTS | 31 | 1 | 30 |  | 96.77%
[7 empty] | Oficina de Logistica | 21 | 2 | 19 |  | 90.48%
[7 empty] | Almacen de Químicos de Logistica | 16 | 1 | 15 |  | 93.75%
[7 empty] | Recepción | 21 | 0 | 21 |  | 100%
[7 empty] | Comedor | 7 | 0 | 7 |  | 100%
[7 empty] | Vestidores | 15 | 0 | 15 |  | 100%
[7 empty] | Control tower | 13 | 4 | 9 |  | 69.23%
[7 empty] | Utilities | 21 | 3 | 18 |  | 85.71%
[7 empty] | Sub Estación de Refrigeración | 21 | 3 | 18 |  | 85.71%
[7 empty] | Sub Estación de Aire & CO2 | 21 | 2 | 19 |  | 90.48%
[7 empty] | Calderas | 21 | 2 | 19 |  | 90.48%
[7 empty] | Tableros | 21 | 2 | 19 |  | 90.48%
[7 empty] | Torre de molienda | 20 | 5 | 15 |  | 75%
[7 empty] | brewhouse | 22 | 5 | 17 |  | 77.27%
[7 empty] | Coldblock | 22 | 4 | 18 |  | 81.82%
[7 empty] | Corredor de Valvulas, CCT | 21 | 4 | 17 |  | 80.95%
[7 empty] | Filtración, BBT | 23 | 4 | 19 |  | 82.61%
[7 empty] | Almacen de Químicos y Bodega de Lupulo | 21 | 3 | 18 |  | 85.71%
[7 empty] | sugar dosing | 22 | 4 | 18 |  | 81.82%
[7 empty] | Recepcion de Granos | 23 | 4 | 19 |  | 82.61%
[7 empty] | Receocion de Químicos de Elaboración | 23 | 4 | 19 |  | 82.61%
[7 empty] | Sub Productos | 22 | 5 | 17 |  | 77.27%
[7 empty] | Total | 45 | 9 | 36 |  | 86.5%
21
4
7
17
95%
88%
88%
89%
0%
95%
0%
86%
83%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Hoja2
0%
| 2025-09-12 | 2025-06-20 |  |  | 2025-09-27 |  |  | 2025-10-04 |  | 2025-10-11 |  | 2025-10-18 |  | 2025-10-25
| REAL | LE | DIF | REAL | LE | DIF | REAL | LE | REAL | LE | REAL | LE | REAL | LE | REAL
Utilities | 91% | 94% | 3% | 93.57% | 97% | 3.428% | 93.57% | 100% |  | 100%
Packaging | 98% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Brewing | 74% | 80% | 6% | 89% | 85% | -4% |  | 90% |  | 95% |  | 97% |  | 100%
Civil | 85% | 88% | 3% | 86% | 92% | 6% | 95% |  | 97% |  | 98% |  | 99%
Logistica | 70% | 76% | 6% | 87% | 82% | -5% | 88% |  | 92% |  | 95% |  | 98%
Enviroment | 34% | 50% | 16% | 53% | 65% | 12% | 75% |  | 85% |  | 90% |  | 95%

## Hoja1
Recibo de Granos | 23 | 22 | 29 | 41 | 38 | 29 | 39 | 28 | 35 | 29 | 24 | 24 | 25 | 18
Silos
Torre de molienda
Brewhouse
Cold Block
CCTs
Filtración
BBTs
Dosificación de azúcar
Edificio Aditivos
Almacenamiento de Lupulo
Corredor de válvulas
Subestación electrica Filtración
Zona Subproductos

## Verificación (hidden)
|  | Brewing | [13 empty] | YES | 29.29%
[16 empty] | NO | 23.37%
[16 empty] | NA | 47.34%
AREAS GENERALES | 58 | Recibo de Granos | Silos | Torre de molienda | Brewhouse | Cold Block | CCTs | Filtración | BBTs | Dosificación de azúcar | Edificio Aditivos | Almacenamiento de Lupulo | Corredor de válvulas | Subestación electrica Filtración | Zona Subproductos | 812 | %
| YES | 11 | 10 | 14 | 23 | 17 | 13 | 21 | 12 | 18 | 13 | 10 | 10 | 11 | 5 | 188 | 23.15%
| NO | 14 | 12 | 16 | 23 | 20 | 14 | 25 | 14 | 20 | 22 | 15 | 13 | 16 | 11 | 235 | 28.94%
| NA | 33 | 36 | 28 | 12 | 21 | 31 | 12 | 32 | 20 | 23 | 33 | 35 | 31 | 42 | 389 | 47.91%
GRAINS HANDLING | 64 | InTake Arroz | In take Malta | Silos | Torre de Molienda | [10 empty] | 256
| Yes | 39 | 39 | 38 | 45 | [10 empty] | 161 | 62.89%
| No | 2 | 2 | 4 | 2 | [10 empty] | 10 | 3.906%
| Na | 23 | 23 | 22 | 17 | [10 empty] | 85 | 33.2%
HOT BLOCK SAFETY | 49 | Brewhouse | Sugar Dosing | Co-products | Energy Recovery | [10 empty] | 196
| Yes | 43 | 22 | 20 | 17 | [10 empty] | 102 | 52.04%
| No | 2 | 1 | 1 | 1 | [10 empty] | 5 | 2.551%
| Na | 4 | 26 | 28 | 31 | [10 empty] | 89 | 45.41%
COLD BLOCK SAFETY | 37 | Yeast Storage | Propagation | Waste Yeast | Opticellar | CCT | Filtration | BBT | DAW | CIP | [5 empty] | 333
| Yes | 7 | 7 | 9 | 15 | 10 | 13 | 11 | 6 | 4 | [5 empty] | 82 | 24.62%
| No | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | [5 empty] | 16 | 4.805%
| Na | 28 | 28 | 26 | 20 | 25 | 22 | 24 | 29 | 33 | [5 empty] | 235 | 70.57%
MACHINE SAFETY | 53 | Mash Filter | Molinos | equip 3 | equip 4 | equip 5 | equip 6 | equip 7 | equip 8 | equip 9 | equip 10 |  |  |  |  | 530
| Yes | 36 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 69 | 13.02%
| No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0%
| Na | 17 | 20 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 |  |  |  |  | 461 | 86.98%
MAINTENANCE SAFETY | 29 | equip / area 1 | equip / area 2 | equip / area 3 | equip / area 4 | equip / area 5 | equip / area 6 | equip / area 7 | equip / area 8 | equip/area 9 | equip / area 10 |  |  |  |  | 290
| Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0%
| No | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 |  |  |  |  | 290 | 100%
| Na | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0%

## Plan de trabajo
| Plan de trabajo 2025 | [9 empty] | Fecha de Entrega final | 2025-10-15
[12 empty] | 2025-09-23 21:21 | 21.1107
| GTS | Totales | Completadas | Faltantes | Avance | Pdte | MES | CIERRE DE FALTANTES | ACCIONES PLANIFICADAS X CIERRE | ACCIONES CERRADAS REAL | ACCIONES ACUMULADAS CERRADAS PROYECIÓN
x | General areas Brewing | 423 | 188 | 235 | 44.44% | 55.56% | 6 | 5% | 100 | 80 | 100 | 0.089833
x | General Areas Packaging | 71 | 0 | 71 | 0% | 100% | 7 | 15% | 300 | 300 | 400 | 0.29733
x | General Areas Utilities | 120 | 49 | 71 | 40.83% | 59.17% | 8 | 35% | 600 | 400 | 1000 | 0.29733
| General Areas Environment | 108 | 38 | 70 | 35.19% | 64.81% | 9 | 65% | 800 | 700 | 1800 | 0.30158
x | General Areas Logistic | 204 | 0 | 204 | 0% | 100% | 10 | 85% | 400 | 200 | 2200 | 0.10348
x | Granins Handing Brewing | 171 | 161 | 10 | 94.15% | 5.848% | 11 | 100% | 135 | 100 | 2335 | 2.1111
x | Hot Block Brewing | 107 | 102 | 5 | 95.33% | 4.673% |  |  | 2335 | 1780 | 76.23% | 4.2221
x | Cold Block Brewing | 98 | 82 | 16 | 83.67% | 16.33% |  |  |  |  | 23.77% | 1.3194
x | Packaging Safety | 83 | 50 | 33 | 60.24% | 39.76% | [5 empty] | 0.63972
| Machine Brewing | 69 | 69 | 0 | 100% | 0%
x | Machine Utilities | 977 | 0 | 977 | 0% | 100% | [5 empty] | 0.021608
| Machine Environment | 92 | 0 | 92 | 0% | 100% | [5 empty] | 0.22946
x | Machine Packaging | 423 | 0 | 423 | 0% | 100% | [5 empty] | 0.049907
x | Steam Utilities | 76 | 41 | 18 | 53.95% | 46.05% | [5 empty] | 1.1728
x | CO2 Utilities | 32 | 0 | 32 | 0% | 100% | [5 empty] | 0.65971
x | Refrigeration Utilities | 72 | 41 | 31 | 56.94% | 43.06% | [5 empty] | 0.68099
x | Compressed air Utilities | 24 | 18 | 6 | 75% | 25% | [5 empty] | 3.5184
x | Logistics Safety | 41 | 0 | 41 | 0% | 100% | [5 empty] | 0.51489
| Totales | 3191 | 839 | 2335 | 26.29% | 73.17% | [5 empty] | 0.009041